## Project 1
Project 1: Telco Churn Model | [9 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
EDA Web Application |  | 2021-07-14 | [7 empty] | COMPANY NAME | [6 empty] | Point Estimation Ltd.
Sourav Das |  | Sourav Das | [7 empty] | DATE | [6 empty] | 2021-08-04
Current Week ➜
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | COMMENTS | PRIORITY | PCT OF TASK COMPLETE | STATUS | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28
[10 empty] | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
Project definition
1.1 | Define requirments | SK | 2021-07-15 | 2021-07-16 | 1 |  |  | 100% | Complete
1.2 | Make project plan | SK | 2021-07-15 | 2021-07-19 | 4 |  |  | 100% | Complete
1.3 | Approve project plan | SD | 2021-07-21 | 2021-07-22 | 1 |  |  | 0% | Running Late
Contents
2.1 | Gather information about EDA steps | SK | 2021-07-15 | 2021-07-20 | 5 |  |  | 100% | Complete
2.2 | Decide framework for project | SK | 2021-07-15 | 2021-07-16 | 1 |  |  | 100% | Complete
2.3 | Write specification (project brief) | SK | 2021-07-16 | 2021-07-19 | 3 |  |  | 100% | Complete
2.4 | Approve brief | SD | 2021-07-21 | 2021-07-22 | 1 |  |  | 0% | Running Late
2.5 |  | SK |  | 1900-01-02 | 3 |  |  | 0% | TBC
2.6 |  | SK |  | 1900-01-06 | 7 |  |  | 0% | TBC
2.7 |  | SK |  | 1900-01-06 | 7 |  |  | 0% | TBC
Web app building
3.1 | Document development | SK | 2021-07-15 |  |  |  |  | 100% | ongoing
3.2 | Set up Github repository | SK | 2021-07-15 | 2021-07-16 | 1 |  |  | 100% | Complete
3.3 | planning (research) | SK | 2021-07-15 | 2021-07-30 | 15 |  |  | 100% | Complete
3.4 | Initial coding (prototype) | SK | 2021-07-21 | 2021-08-15 | 25 |  |  | 50% | Running Late
3.5 | approve initial programme | SD | 2021-08-16 | 2021-08-17 | 1 |  |  | 0% | Yet to Start
3.6 | Add changes and improvements | SK | 2021-08-17 | 2021-08-20 | 3 |  |  | 0% | Yet to Start
3.7 | approve changes | SK | 2021-08-20 | 2021-08-21 | 1 |  |  | 0% | Yet to Start
3.8 | Testing | SK | 2021-08-20 | 2021-08-21 | 1 |  |  | 0% | Yet to Start
|  |  |  | 0 |  |  |  |  | TBC
|  |  |  | 0 |  |  |  |  | TBC
Presentation
4.1 | Presentation Planner | SK | 2021-08-21 | 2021-08-22 | 1 |  |  | 0% | Yet to Start
4.2 | Create presentation | SK | 2021-08-22 | 2021-08-25 | 3 |  |  | 0% | Yet to Start
4.3 | Present presentation to manager | SK | 2021-08-26 | 2021-08-27 | 1 |  |  | 0% | Yet to Start
4.4 | De-brief | SK